## Sheet1
classification	name	pirority	estimation in hour	furtur explanation
	update reciept structure	A	16	blocking
	async logging	A+	16	blocking
	update protobufs	A	36	blocking
	clean up login	A	16	slow development bug prone
	Clean up KYC APIs	A	36	slow development bug prone
	major refactoring	B	48	bug prone
	Using kafka for internal communication	A	36	most have before public lunch
	protobuf validation	A	24

Security phase 2	move security related checking into spring security	B	36	blocking
Security phase 2	persisting device information	A	8	blocking
Security phase 2	otp for new devices	B	16
Security phase 2	support tickets for clients	C	8
Security phase 2	block sensitive headers from clients	A	8
Security phase 2	encrypt jwt tokens with AES keys from client	B	8

development	server driven UI for error presentation	C	24
development	get user profile	A+	8	blocking
development	complementry information for transactions	C	24
development	payment tree structure	B	24
development	identify bill issuer company	C	8
development	special cases in kyc	C	16	unknown issues that might raise

Architecture	seperate outbound modules into microservices	B	100
Architecture	remove experimental feature	A	8
Architecture	overhaul our test system	A	200	critical to ensure proper deployments and remove possible breaking changes